## Sheet1
Test Case ID	Issue Date	Retest Date	Closed Date	Severity	Status	Developer Status	QK Status	Remark	Steps	Ageing	Comment	RefID	Mobile Number	Evidance
49	01/02/24			Medium	Open	Reported			1.Open Dairy Loan URL in Browser. / 2.Login Home page will open. / 3.Login with OTP. / 4.Pre-Approved Loan Details will open. / 5.Click on Accept Button. / 6.Loan Requirement Page will Open. / 7.Enter Value in all Fields. / 8.In Bank Use Only Screen In Distance From Branch Enter Invalid Values or Keep field Blank.		No validation error message at RM distance from Branch.	50224000013	9023036757
50	01/02/24			Medium	Open	Reported			1.Open Dairy Loan URL in Browser. / 2.Login Home page will open. / 3.Login with OTP. / 4.Pre-Approved Loan Details will open. / 5.Click on Accept Button. / 6.Loan Requirement Page will Open. / 7.Enter Value in all Fields. / 8.In Bank Use Only Screen In Distance From RM Location Enter Invalid Values or Keep field Blank.		Distance from branch and RM Location Control	50224000013	9023036757
51	01/02/24			Medium	Open	Reported			1.Open Dairy Loan URL in Browser. / 2.Login Home page will open. / 3.Login with OTP. / 4.Pre-Approved Loan Details will open. / 5.Click on Accept Button. / 6.Loan Requirement Page will Open. / 7.Enter Value in all Fields. / 8.In Bank Use Only Screen RO/SO Recommendation Field.		RM Recommendation not checked then also case processed	50224000013	9023036757
77	01/02/24			Medium	Open	Reported			1.Open Dairy Loan URL in Browser. / 2.Login with Mobile Number and OTP. / 3.Fill Loan Requirement Details. / 4.Click on Start Loan Application Button. / 5.Personal Loan Information Screen will Open. / 6.Fill all details in Location details,Additional Details & Verify Account Details. / 7. Additional KYC- Select Voter ID / 8. Enter Voter ID / 9.Click on Save & Continue Button.		Voter ID Check not happened – RIO1933373, Even after deviation still the case got moved.	50224000013	9023036757
107	01/02/24			Medium	Open	Reported			1.Open Dairy Loan URL in Browser. / 2.Login with Mobile Number and OTP. / 3.Fill Loan Requirement Details. / 4.Click on Start Loan Application Button. / 5.Fill Personal Loan Information & Land Details. 6.Click on Save & Continue Button. / 7.Income Page will be open. / 8. Enter Cattle count in the field.		Existing Cattle control not required.	50224000013	9023036757